## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled |  | 2801 days? | 05 January 2015 8:00 SA | 29 September 2025 5:00 CH |  | 0
1 | Yes | Manually Scheduled | Planning phase | 11 days | 05 January 2015 8:00 SA | 19 January 2015 5:00 CH |  | 1
2 | Yes | Auto Scheduled | Assign launch team members | 1 day | 05 January 2015 8:00 SA | 05 January 2015 5:00 CH |  | 2
3 | Yes | Auto Scheduled | Design and order marketing material | 2 wks | 05 January 2015 8:00 SA | 16 January 2015 5:00 CH |  | 2
4 | Yes | Auto Scheduled | Planning complete! | 0 days | 05 January 2015 8:00 SA | 05 January 2015 8:00 SA |  | 2
5 | Yes | Auto Scheduled | Public Launch Phase | 11 days? | 15 September 2025 8:00 SA | 29 September 2025 5:00 CH |  | 1
6 | Yes | Auto Scheduled | Distribute advance copies | 2 days | 15 September 2025 8:00 SA | 16 September 2025 5:00 CH |  | 2 | Get recipient list from publicist
7 | Yes | Auto Scheduled | Coordinate magazine feature articles | 7 days | 17 September 2025 8:00 SA | 25 September 2025 5:00 CH | 6 | 2
8 | Yes | Auto Scheduled | Launch public web portal for book | 1 day? | 26 September 2025 8:00 SA | 26 September 2025 5:00 CH | 7 | 2
9 | Yes | Auto Scheduled | Launch social media programs for book | 1 day | 29 September 2025 8:00 SA | 29 September 2025 5:00 CH | 8 | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | 0,00 ₫/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units